| ITEMS | QUALITY | ESTIMATED AMOUNT | Actual |
| --- | --- | --- | --- |
| Transport and interview dancers | 6 trips (R15 per trip for 3 people) | R150 | R90 |
| Data for uploads and research | 20GB | R100 | R120 |
| Printing permission letter | 2 pages | R4 | R4 |
| Tripod stand | 1 | R120 | R120 |
| Phone camera | 1 | R0 | R0 |
| Bottled water | 3 | R45 | R36 |
| Powerades | 3 | R45 | R54 |
| Snack Packs | 3 | R75 | R75 |
| Website cost | 1 | R120 | R0 |
| TOTAL |  | R659.00 | R499.00 |

# Budget

All money that we expected to spend

Budget Performance

The project budget was estimated at R734. Actual expenditure was R499, representing a 32% saving. Major savings were achieved on transport (R60) and website costs (R100) due to selecting a free platform. The only over-expenditure was R120 on data due to larger video file sizes. All other items were on or under budget. No contingency funds were used.

What went well

•  We saved R100 by using a free Google site instead of a paid website, with no impact on project objectives.

•  Using personal phones for filming resulted in R0 equipment cost.

•  Overall we were 32% under budget, showing good cost control.

Lessons learned:

•  Data costs are hard to predict for video projects. Recommend budgeting 20% extra for data in future.

•  Transport estimates should be based on actual taxi quotes, not guesses.